## Epic
Issue Type | Key | Summary | Status | Assignee | Created | Updated | Reporter
Epic | GW-1 | Accoount Regstiry and login | Done | ahmed osman | 2025-03-10 | 2025-04-11 | ahmed osman
Epic | GW-2 | Booking and Trip Management | Done | ahmed osman | 2025-03-10 | 2025-04-11 | ahmed osman
Epic | GW-3 | Payments | Done | Ahmed Sayed Abdullah | 2025-03-10 | 2025-04-11 | ahmed osman
Epic | GW-4 | User Experience and Website Interface | Done | asmaa elshafey | 2025-03-10 | 2025-04-11 | ahmed osman
Epic | GW-5 | Mange account and Customer Support | Done | Nada Nasser Shaban | 2025-03-10 | 2025-04-11 | ahmed osman
Epic | GW-6 | Travel Routes and Go Bus Categories | Done | Mohamed Mahmoud Amen | 2025-03-10 | 2025-03-29 | ahmed osman

## Task
Issue Type | Key | Summary | Status | Assignee | Created | Updated | Reporter
Task | GW-61 | [TC15][Responsiveness ][Verify website desktop responsiveness ] | pass | asmaa elshafey | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-60 | [TC14][Responsiveness ][Verify website mobile responsiveness ] | pass | asmaa elshafey | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-59 | [TC13][Go Bus App button ][Verify App store button functionality] | failed | asmaa elshafey | 2025-03-25 | 2025-03-30 | ahmed osman
Task | GW-58 | [TC12][Go Bus App button ][Verify google play button functionality] | pass | asmaa elshafey | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-57 | [TC11][Menu Tabs ][Verify links of menu tabs functionality in mobile] | failed | asmaa elshafey | 2025-03-25 | 2025-03-30 | ahmed osman
Task | GW-56 | [TC10][Menu Tabs ][Verify links of menu tabs functionality in desktop] | pass | asmaa elshafey | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-54 | [TC08][Social Media Buttons][Verify WhatsApp link] | pass | asmaa elshafey | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-53 | [TC07][Social Media Buttons][Verify YouTube link] | pass | asmaa elshafey | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-52 | [TC06][Social Media Buttons][Verify LinkedIn link] | pass | asmaa elshafey | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-51 | [TC05][Social Media Buttons][Verify Instagram link] | pass | asmaa elshafey | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-50 | [TC04][Social Media Buttons][Verify Facebook link] | failed | asmaa elshafey | 2025-03-25 | 2025-03-30 | ahmed osman
Task | GW-28 | [TC03][Sidebar][Verify Sidebar Navigation links Functionality] | pass | asmaa elshafey | 2025-03-24 | 2025-03-25 | ahmed osman
Task | GW-27 | [TC02][Footer][Verify Footer Navigation links and Go Bus icon Functionality] | pass | asmaa elshafey | 2025-03-24 | 2025-03-25 | ahmed osman
Task | GW-30 | [TC03][Registration][Verify that the name field not accpted number ] | failed | ahmed osman | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-26 | [TC01][Header][Verify Header Navigation links and Go Bus icon Functionality] | pass | asmaa elshafey | 2025-03-24 | 2025-03-25 | ahmed osman
Task | GW-23 | [TC01][Registration] Verify that the name field with vaild name | pass | ahmed osman | 2025-03-24 | 2025-03-25 | ahmed osman
Task | GW-29 | [TC02][Registration][ Verify that not resgrity same date ] | pass | ahmed osman | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-34 | [TC01][Searching for Trips][Search with default “From” and “To”] | pass | Youssef Mustafa | 2025-03-25 | 2025-04-06 | ahmed osman
Task | GW-32 | [TC04][Registration][Verify that the name field not accpted blank field] | pass | ahmed osman | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-33 | [TC05][Registration][Verify that the phone number field not accpted letter ] | pass | ahmed osman | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-25 | [TC02][My Account]: Verify Booking Cancellation in User Profile | failed | Nada Nasser Shaban | 2025-03-24 | 2025-04-06 | ahmed osman
Task | GW-24 | [TC01][My Account]:[Verify Booking Details in User Profile] | pass | Nada Nasser Shaban | 2025-03-24 | 2025-03-27 | ahmed osman
Task | GW-35 | [TC02][Searching for Trips][Change “From” and “To” from defaults] | pass | Youssef Mustafa | 2025-03-25 | 2025-04-06 | ahmed osman
Task | GW-36 | [TC03][Searching for Trips][Search with the same “From” and “To” ] | pass | Youssef Mustafa | 2025-03-25 | 2025-04-06 | ahmed osman
Task | GW-37 | [TC04][Searching for Trips][Search with no passenger number below 1 (minimum is 1)] | pass | Youssef Mustafa | 2025-03-25 | 2025-04-06 | ahmed osman
Task | GW-38 | [TC05][Searching for Trips][Search for multiple passengers] | pass | Youssef Mustafa | 2025-03-25 | 2025-04-06 | ahmed osman
Task | GW-39 | [TC06][Searching for Trips][Search for Round Trip] | pass | Youssef Mustafa | 2025-03-25 | 2025-04-06 | ahmed osman
Task | GW-40 | [TC07][Searching for Trips][Search with invalid date format ] | pass | Youssef Mustafa | 2025-03-25 | 2025-04-06 | ahmed osman
Task | GW-42 | [TC08][Selecting & Booking][Select available seats] | pass | Youssef Mustafa | 2025-03-25 | 2025-04-06 | ahmed osman
Task | GW-43 | [TC09][Selecting & Booking][Attempt to select fully booked seats] | pass | Youssef Mustafa | 2025-03-25 | 2025-04-06 | ahmed osman
Task | GW-48 | [TC10][Selecting & Booking][Verify round-trip discount is applied] | pass | Youssef Mustafa | 2025-03-25 | 2025-04-07 | ahmed osman
Task | GW-62 | [TC05][Registration][Verify that the phone number field not accpted letter ] | pass | ahmed osman | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-64 | [TC07][Registration][Verify that the phone number field not accpted blank field] | pass | ahmed osman | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-63 | [TC06][Registration][Verify that the phone number field not accpted invaild length ] | failed | ahmed osman | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-66 | [TC09][Registration][Verify that the e-mail field not accpted blank field] | pass | ahmed osman | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-67 | [TC10][Registration][Verify that the password field not accpted week password] | pass | ahmed osman | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-65 | [TC08][Registration]["Verify that the email field only accepts valid email addresses from known services (e.g., Gmail, Yahoo) and rejects temporary email services."] | failed | ahmed osman | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-68 | [TC10][Registration][Verify that the password field not accpted week password] | failed | ahmed osman | 2025-03-25 | 2025-03-30 | ahmed osman
Task | GW-69 | [TC11][Registration][Verify that password field not accpted blank field] | pass | ahmed osman | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-70 | [TC12][login][Login with Valid Email and Valid Password] | pass | ahmed osman | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-71 | [TC13][login][Login with invalid Email and invalid Password] | pass | ahmed osman | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-72 | [TC14][login][Login with inValid Email and Valid Password] | pass | ahmed osman | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-73 | [TC15][login][Login with Valid Email and invalid Password] | pass | ahmed osman | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-74 | [TC16][login][Login with blank Email and vaild Password] | pass | ahmed osman | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-75 | [TC17][login][Login with vaild Email and blank Password] | pass | ahmed osman | 2025-03-25 | 2025-03-25 | ahmed osman
Task | GW-76 | [TC03][My Account][Verify Multiple Bookings in User Profile] | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-27 | ahmed osman
Task | GW-77 | [TC04][My Account][Verify Partial Cancellation of Multiple Bookings] | failed | Nada Nasser Shaban | 2025-03-25 | 2025-03-27 | ahmed osman
Task | GW-78 | [TC05][My Account][Verify Booking Status When Payment is Not Completed] | failed | Nada Nasser Shaban | 2025-03-25 | 2025-03-30 | ahmed osman
Task | GW-79 | [TC06] [My Account] [Verify Booking Confirmation Email] | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-30 | ahmed osman
Task | GW-80 | [TC07] [My Account] [Verify Booking Cancellation Email] | failed | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-81 | [TC08] [My Accoun] [Verify Contact Us Form Submission] | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-83 | [TC09] [My Account] [Verify Contact Us Form Validation] | failed | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-84 | [TC010] [My Account] [Verify Contact Us Page Content] | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-85 | [TC011] [My Account] [Verify Phone Call Support[ | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-30 | ahmed osman
Task | GW-86 | [TC012] [My Account] [Verify WhatsApp Support] | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-87 | [TC013] [My Account] [Verify Email Support] | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-88 | [TC014] [My Account] [Verify Profile Information Display] | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-89 | [TC015] [My Account] [Verify Editing Profile Information with changes] | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-90 | [TC016] [My Account] [Verify Editing Profile Information without Changes] | failed | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-91 | [TC017][My Account ][ Verify Change Password Page Display[ | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-92 | [TC018] [My Account] [Verify Change Password with Valid Data] | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-93 | [TC019] [My Account] [Verify Change Password with Invalid Data] | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-94 | [TC020] [My Account] [Verify Change Password with Incomplete Data] | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-95 | [TC021] [My Account] [Verify Log Out Functionality] | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-96 | [TC022] [My Account] [Verify Log Out from Multiple Pages] | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-97 | [TC023] [My Account] [Verify Log Out with Multiple Tabs Open] | pass | Nada Nasser Shaban | 2025-03-25 | 2025-03-26 | ahmed osman
Task | GW-105 | [TC03][Travel Routes][verify that 'FROM' buttom in searching table is working while use the site as guest] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-106 | [TC04][Travel Routes][verify that 'FROM' buttom in searching table is working whien logged in] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-107 | [TC05][Travel Routes][verify that 'TO' buttom in searching table is working while use the site as guest] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-108 | [TC06][Travel Routes][verify that 'TO' buttom in searching table is working whien logged in] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-109 | [TC07][Travel Routes][verify that 'Departure Date' buttom in searching table is working while use the site as guest] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-110 | [TC08][Travel Routes][verify that 'Departure Date' buttom in searching table is working whien logged in] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-111 | [TC09][Travel Routes][verify that 'Return Date' buttom in searching table is working while use the site as guest] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-112 | [TC010][Travel Routes][verify that 'Return Date' buttom in searching table is working whien logged in] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-113 | [TC011][Travel Routes][verify that 'Passengers' buttom in searching table is working while use the site as guest] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-114 | [TC012][Travel Routes][verify that 'Passengers' buttom in searching table is working whien logged in] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-115 | [TC013][Travel Routes][verify that the trip details are appears while use site as a guest] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-116 | [TC014][Travel Routes][verify that the trip details are appears when logged in] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-117 | [TC015][Go Bus Classes][verify that the all categories are displayed while use the site as a guest] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-118 | [TC016][Go Bus Classes][verify that the all categories are displayed when logged in] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-119 | [TC017][Go Bus Classes][verify that all services are different between categories while using the site as a guest] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-120 | [TC018][Go Bus Classes][verify that all services are diffrent between categories when logged in] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-121 | [TC019][Go Bus Classes][verify that all services are diffrent between categories while using the site as a guest] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-122 | [TC020][Go Bus Classes][verify that all services are diffrent between categories when logged in] | pass | Mohamed Mahmoud Amen | 2025-03-29 | 2025-03-29 | ahmed osman
Task | GW-127 | [TC01] [Payments] Verify Visa Payment Option is Available | pass | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-06 | ahmed osman
Task | GW-128 | [TC02] [Payments] Verify MasterCard Payment Option is Available | pass | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-06 | ahmed osman
Task | GW-129 | [TC03] [Payments] Verify Cash Machines Payment Option is Available | pass | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-06 | ahmed osman
Task | GW-130 | [TC04] [Payments] Verify Error Message for Invalid Credit Card Name | failed | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-11 | ahmed osman
Task | GW-131 | [TC05] [Payments] Verify Error Message for Invalid Credit Card Expiration Date | failed | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-11 | ahmed osman
Task | GW-132 | [TC06] [Payments] Verify Error Message for Empty or Invalid Credit Card CVV Code | failed | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-11 | ahmed osman
Task | GW-133 | [TC07] [Payments] Verify Error Message for Expired Credit Card | failed | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-11 | ahmed osman
Task | GW-134 | [TC08] [Payments] Verify Error Message for Incorrect Card Type (e.g., Visa vs. MasterCard) | pass | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-06 | ahmed osman
Task | GW-135 | [TC09] [Payments] Verify Error Message for Card Number with Invalid Length | pass | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-06 | ahmed osman
Task | GW-136 | [TC10] [Payments] Verify Error Message for Card Number with Non-Numeric Characters | pass | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-06 | ahmed osman
Task | GW-137 | [TC11] [Payments] Verify Error Message for Empty Credit Card Number Field | pass | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-06 | ahmed osman
Task | GW-139 | [TC12] [Payments] Verify entering valid Promo Code | pass | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-11 | ahmed osman
Task | GW-140 | [TC13] [Payments] Verify entering invalid Promo Code | pass | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-11 | ahmed osman
Task | GW-141 | [TC14] [Payments] Verify Promo Code Expiration | pass | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-11 | ahmed osman
Task | GW-142 | [TC15] [Payments] Verify Accepting All Terms & Conditions | pass | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-11 | ahmed osman
Task | GW-143 | [TC16] [Payments] Verify All Terms & Conditions Checkbox (Unchecked) | pass | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-11 | ahmed osman
Task | GW-144 | [TC17] [Payments] Verify that booking a ticket for someone else function is working correctly | pass | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-11 | ahmed osman
Task | GW-145 | [TC18] [Payments] Verify that "Report a bug" function is working correctly | pass | Ahmed Sayed Abdullah | 2025-03-30 | 2025-04-11 | ahmed osman